## TaskList
Task List Report 2 - Preview / Review (Week 2)
Team No. |  | 2 |  | Est. | Act. | Supervisor | Mr Alex Toh
Team Member |  | Lucas Nguyen Thai Vinh | M1 | 20 | 24 | From | 2017-02-13
|  | Lim ZiYi Jean | M2 | 11 | 15 | To | 2017-03-03
|  | Shishanth Kaliannan | M3 | 14 | 14 | Preview | 2017-02-20
|  | Gabriel | M4 | 5 | 5 | Review | 2017-02-27
Preview | [7 empty] | Description of Task | Review
No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
1 | Collision Detection |  | M1 | 5 |  |  |  |  | M1 | 5
2 | Fix enemy algorithm |  | M3 | 3 | There are still some issues with enemy movements and collision with each other, and with objects |  |  |  | M3 | 3
3 | Enemy Collision with player |  | M3 | 3 |  |  |  | Make sure enemy does not collide with player | M3 | 3
4 | Scene Manager |  | M1 | 5 |  |  |  | Changing scenes with sceneManager | M1 | 5
5 | Plaformer mechanics |  | M1 | 6 |  |  |  | Randomise platform, make sure that the player cannot collide with the platforms, and also ensure that there is gravity | M1 | 10 | There are a lot of thinking process through. It was difficult to randomise platforms and map it out. Also, I didn't know how to position the platforms in a way such that they are not close together.
6 | Special Abilities (Platformer) |  | M1 | 4 |  |  |  | Add in optional special abilites for the player to purchase to use in game (e.g double jump, super speed and higher jump) | M1 | 4
7 | Create trigger (UFO kill trigger) |  | M4 | 2 |  |  |  |  | M4 | 2
8 | Shooting mechanic |  | M2 | 6 |  |  |  | Ensure that the rendered gun moves with the player, and the laser beam can collide with surrounding enemies. | M2 | 8 | Increase workload point because there was still some issues with enemy algorith.
9 | Driving mechanic |  | M3 | 5 |  |  |  | Make sure the car can accelerrate, decelerrate and turn smoothly with the player | M3 | 5
10 | Health system |  | M2 | 2 |  |  |  | Design and implement health system for mini games | M2 | 3
11 | Currency system |  | M2 | 3 |  |  |  | Design a currency system that is to be used throughout the whole gane | M2 | 4
12 | Projectile function |  | M4 | 3 |  |  |  |  | M4 | 3
13 | Health and fuel(driving) |  | M3 | 3 |  |  |  | Have a visual of player's health and fuel bar | M3 | 3
Total |  |  |  | 50 | [5 empty] | 58
Comments for preview | [8 empty] | Comments for review
(Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
Lucas Nguyen Thai Vinh |  |  |  | Lim ZiYi Jean |  |  |  |  | Lucas Nguyen Thai Vinh |  |  | Lim ZiYi Jean
Shishanth Kaliannan |  |  |  | Gabriel |  |  |  |  | Shishanth Kaliannan |  |  | Gabriel