## TaskList
Task List Report 3 - Preview / Review (Week 3)
Team No. |  | 2 |  | Est. | Act. | Supervisor | Mr Alex Toh
Team Member |  | Lucas Nguyen Thai Vinh | M1 | 11 | 11 | From | 2017-02-13
|  | Lim ZiYi Jean | M2 | 21 | 25 | To | 2017-03-03
|  | Shishanth Kaliannan | M3 | 12 | 12 | Preview | 2017-02-27
|  | Gabriel | M4 | 10 | 10 | Review | 2017-03-02
Preview | [7 empty] | Description of Task | Review
No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
1 | Hit Detection(spaceship) |  | M4 | 3 |  |  |  | Make sure that the ships do not collide with each other | M4 | 3
2 | Sound |  | M3 | 4 |  |  |  | Put in sounds for the game | M3 | 3 | Had some help from friends
3 | File Reading |  | M2 | 3 |  |  |  | Read from notepad to render text on screen | M2 | 4 | Forgot that the renderTextToScreen only reads character by character
4 | Fence |  | M2 | 1 |  |  |  | Build a fence in maya to surround the whole main scene | M2 | 1
5 | Pause and game over design |  | M4 | 1 |  |  |  | Design pause and game over scren | M4, M2 | 1 | M1 only designed game over screen for platform and shooting. M4 designed the rest
6 | Fixing bug |  | M1, M2, M3, M4 | 3 |  |  |  | Play the game thoroughly and fix whatever warnings there are. Remove any externs and try to do it some other way | M1, M2, M3, M4 | 3
7 | Trailer |  | M2 | 1 |  |  |  |  | M2 | 1
8 | Documentations update |  | M2 | 5 |  |  |  |  | M2 | 7 | There are a lot of things to update
9 | Putting in pause and game over screens into program |  | M1 | 5 |  |  |  | Allow player to be able to pause the game to resume or exit. Also ensures there is game over screen that allows user to either retry or exit | M1 | 5 | There were some small bugs like, didnt see that the program was rendering a NULL mesh
10 | Tidy up and comment out codes |  | M1, M2, M3, M4 | 3 |  |  |  | Organise by putting codes into functions and seperate various codes with "======" as a divider for better view | M1, M2, M3, M4 | 3
11 | Tutorial (shooting) |  | M2 | 5 |  |  |  | Add in a sequential tutorial that is affected either by display time or player's actions. | M2 | 5
12 | Put in guide into select menu |  | M3 | 2 |  |  |  |  | M3 | 2
Total |  |  |  | 36 | [5 empty] | 38
Comments for preview | [8 empty] | Comments for review
(Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
Lucas Nguyen Thai Vinh |  |  |  | Lim ZiYi Jean |  |  |  |  | Lucas Nguyen Thai Vinh |  |  | Lim ZiYi Jean
Shishanth Kaliannan |  |  |  | Gabriel |  |  |  |  | Shishanth Kaliannan |  |  | Gabriel