## Sheet1
| 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02
Proposal | [14 empty] | Member | Colour | bar: 2017-02-13
Mouse Input | [14 empty] | Lucas | bar: 2017-02-13 to 2017-02-15
Bounds checking | [14 empty] | Jean | bar: 2017-02-13 to 2017-02-14
Character Movement | [14 empty] | Shishanth | bar: 2017-02-13 to 2017-02-15
Building design | [14 empty] | Gabriel | bar: 2017-02-13 to 2017-02-15
Skybox | bar: 2017-02-14 to 2017-02-17
Collision detection | bar: 2017-02-14 to 2017-02-21
Space Craft (Player) | bar: 2017-02-14
Space Craft (NPC) | bar: 2017-02-14
Main Menu coding and design | bar: 2017-02-15 to 2017-02-17
Enemy Algorithm | bar: 2017-02-15 to 2017-02-22
Camera (Spaceship) | bar: 2017-02-15 to 2017-02-16
Random spawning of NPC (Spaceship) | bar: 2017-02-16 to 2017-02-20
Enemy Collision with player | bar: 2017-02-17 to 2017-02-21
Scene manager | bar: 2017-02-17 to 2017-02-20
Player collision with enemies (shooting) | bar: 2017-02-17
Platformer Mechanics / Special Abilities | bar: 2017-02-20 to 2017-02-28
Create trigger (UFO kill trigger) | bar: 2017-02-20 to 2017-02-21
Shooting mechanic | bar: 2017-02-20 to 2017-02-23
Driving mechanic | bar: 2017-02-21 to 2017-02-24
Health System | bar: 2017-02-21 to 2017-02-22
Currency System | bar: 2017-02-22 to 2017-02-24
projectile function | bar: 2017-02-22 to 2017-02-27
Health and fuel (driving) | bar: 2017-02-24 to 2017-02-27
Hit detection (Spaceship) | bar: 2017-02-27 to 2017-02-28
Sound | bar: 2017-02-27 to 2017-03-02
File Reading | bar: 2017-02-27 to 2017-02-28
Fence (Main menu) | bar: 2017-03-01
Pause & game over design | bar: 2017-03-01
Fixing bugs | bar: 2017-03-02
Trailer | bar: 2017-03-02
Music | bar: 2017-03-02
Document updates + final | bar: 2017-03-02