## TaskList
Task List Report 1 - Preview / Review (Week 1)
Team No. |  | 2 |  | Est. | Act. | Supervisor | Mr Alex Toh
Team Member |  | Lucas Nguyen Thai Vinh | M1 | 8 | 18 | From | 2017-02-13
|  | Lim ZiYi Jean | M2 | 16 | 19
|  | Shishanth Kaliannan | M3 | 14 | 20 | To | 2017-03-03
|  | Gabriel | M4 | 9 | 11 | Preview | 2017-02-13
[6 empty] | Review | 2017-02-20
Preview | [7 empty] | Description of Task | Review
No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
1 | Proposal |  | M1, M2, M3, M4 | 2 |  |  |  | Come up with proposal for game, gnatt chart and product backlog. Everyone has to contribue. | M1, M2, M3 | 2 | Did the product backlog and the initial gnatt chart
2 | Mouse Input |  | M3 | 4 |  |  |  | Put in mouse input for game | M3 | 5 | Mouse input was done. However, it still has some issues
3 | Bounds Checking |  | M1 | 2 |  |  |  | Make sure the player cannot walk out of skybox | M1 | 2
4 | Character Movement |  | M2 | 2 |  |  |  | Put in limits as to how the character will be able to move | M2 | 2
5 | Building and carousel design |  | M2 | 3 |  |  |  | Design buildings that player can enter, and make a carousel such that it can rotate at the bottom | M2 | 3
6 | Skybox |  | M1, M2, M3, M4 | 2 |  |  |  | Everyone has to find their own skybox for their game | M1, M2, M3, M4 | 2
7 | Collision detection |  | M2 | 4 |  |  |  | Put in AABB collision detection between player and buildings in the main scene | M1 | 6 | At first, the collision was using a sphere to check for collision. However, it had a little bug. Hence, M1 took over and used AABB collision instead. AABB took much longer to implement compared to using a sphere.
8 | Design space craft |  | M4 | 2 |  |  |  | Design space craft in maya | M4 | 2
9 | Main menu |  | M2 | 4 |  |  |  | Design how the main menu will look like, and ensure that it is able to enter the scene through main menu | M2 | 4
10 | Enemy Algorithm |  | M3 | 6 |  |  |  | Determine enemy movements and make that they dont collide with each other | M3 | 8 | Code is hard to read. M1 optimised the code a little by reducing three "for" loops(100x500x500) down to one "for" loop(enemy size)
11 | Spaceship camera |  | M4 | 3 |  |  |  | Make azimuth camera for spaceship scene | M4 | 3
12 | Random spawning of spaceship |  | M4 | 4 |  |  |  |  | M4 | 4
13 | Enemy collision with player |  | M3 | 4 |  |  |  | Make sure that enemies cannot pass through player | M3 | 3
14 | Scene manager |  | M1 | 6 |  |  |  |  | M1 | 6
15 | Player's collision with enemy |  | M2 | 3 |  |  |  | Ensure that player cannot walk pass enemies | M2 | 3
16
17
18
Total |  |  |  | 51 | [5 empty] | 55
Comments for preview | [8 empty] | Comments for review
(Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
Lucas Nguyen Thai Vinh |  |  |  | Lim ZiYi Jean |  |  |  |  | Lucas Nguyen Thai Vinh |  |  | Lim ZiYi Jean
#REF! | [8 empty] | #REF!